## Slide 1
Agile Development & Scrum
敏捷开发与 Scrum
Week 3 — Delivering value in a changing world 在变化的世界中持续交付价值
Software Engineering I · 32 hours · 16 weeks 软件工程 I · 32 学时 · 16 周
International Bilingual Class, 29 students 国际双语班 29 人
Textbook: Pressman, Software Engineering: A Practitioner’s Approach 教材：Pressman《软件工程：实践者的方法》

## Slide 2
Contents
目录
01 A. Review & Motivation 回顾与导入
02 B. The Agile Mindset 敏捷思想
03 C. The Scrum Framework Scrum 框架
04 D. Class Activities 课堂活动
Software Engineering I · 2026-2027-1 · Ren Zheng
2

## Slide 3
Part A
Review & Motivation 回顾与导入
Where we left off — and what still hurts 回顾上节课，引出敏捷的动因

## Slide 4
Last Week Recap
上节课回顾
▪ A software process = framework + umbrella activities 软件过程 = 框架活动 + 伞形活动
▪ Classic models: waterfall, V, incremental, prototyping, spiral, concurrent, RUP 经典模型一览
▪ Choosing a model depends on: requirement certainty, risk, scale, delivery needs 选型取决于需求明确度、风险、规模与交付要求
▪ Open question 遗留问题:
▪ • What if requirements keep changing and the customer wants results fast? 如果需求持续变化、客户又要快速见效怎么办？
Software Engineering I · 2026-2027-1 · Ren Zheng
4

## Slide 5
Learning Outcomes
本课目标
▪ State the 4 values of the Agile Manifesto and the core of the 12 principles 说出敏捷宣言 4 条价值观与 12 条原则的核心
▪ Identify what all agile processes share: adaptability, rapid delivery, human collaboration 概括敏捷过程的共性
▪ Describe Scrum roles, artifacts, events, and the sprint cycle 描述 Scrum 的角色、工件、活动与冲刺循环
▪ Decide when agile fits — and when it does not 判断敏捷的适用与不适用情境
▪ Draft user stories for your SafeHome project (Exercise 2) 为 SafeHome 起草用户故事（练习2）
Software Engineering I · 2026-2027-1 · Ren Zheng
5

## Slide 6
Why Agile Exists
敏捷为何而生
▪ Software projects fail most often from: changing requirements, late feedback, oversized plans 软件项目最常见的失败原因：需求变化、反馈太晚、计划过大
▪ Real-world pressures 现实压力:
▪ • Customers cannot state all needs up front 客户无法预先说清全部需求
▪ • Markets move while heavy documents are being written 市场在厚重文档写成之前已经变了
▪ • Working software after 12 months is worth less than a demo after 2 weeks 12 个月后的完整软件，常常不如 2 周后的演示有价值
▪ Agile answers: short cycles, continuous feedback, embrace change 敏捷的回答：短周期、持续反馈、拥抱变化
Software Engineering I · 2026-2027-1 · Ren Zheng
6

## Slide 7
Part B
The Agile Mindset 敏捷思想
Values and principles before practices 先讲价值观与原则，再谈实践

## Slide 8
The Agile Manifesto (2001)
敏捷宣言的诞生
▪ February 2001, Snowbird ski lodge, Utah — 17 practitioners of “lightweight methods” 2001 年 2 月，美国犹他州雪鸟滑雪场，17 位轻量级方法实践者
▪ They found common ground despite different methods (XP, Scrum, Crystal, FDD …) 尽管方法各异（XP、Scrum、Crystal…），他们找到了共识
▪ The result: 4 values + 12 principles — a mindset, not a concrete process 成果：4 条价值观 + 12 条原则——是一种理念，不是具体过程
▪ “Agile” became the umbrella name for this family of methods “敏捷”从此成为这一方法家族的统称
Software Engineering I · 2026-2027-1 · Ren Zheng
8

## Slide 9
The 4 Values
四条价值观
Individuals & interactions
个体与互动
over
Processes & tools
流程与工具
Working software
可运行的软件
over
Comprehensive documentation
详尽的文档
Customer collaboration
客户协作
over
Contract negotiation
合同谈判
Responding to change
响应变化
over
Following a plan
遵循计划
The Agile Manifesto (2001) — value the items on the left more 宣言：虽然右项也有价值，我们更重视左项
“While there is value in the items on the right, we value the items on the left more.”
Read as: we value the left more — not “only the left” 解读：更重视左项，而非“只要左项”
Software Engineering I · 2026-2027-1 · Ren Zheng
9

## Slide 10
12 Principles — the Essentials
12 条原则（精选）
▪ Our highest priority: satisfy the customer through early and continuous delivery 最高优先级：通过尽早且持续地交付让客户满意
▪ Welcome changing requirements, even late in development 欢迎需求变化，哪怕在开发后期
▪ Business people and developers must work together daily 业务人员与开发人员必须每日协作
▪ Build projects around motivated individuals; trust and support them 以有积极性的个体为核心构建项目，给予信任与支持
▪ Face-to-face conversation is the best form of communication 面对面交谈是最好的沟通方式
▪ Sustainable pace — able to maintain a constant pace indefinitely 可持续的节奏，能长期保持恒定步调
▪ At regular intervals, the team reflects and adjusts — continuous improvement 定期回顾与调整——持续改进
Software Engineering I · 2026-2027-1 · Ren Zheng
10

## Slide 11
What Is Agility?
什么是敏捷（Pressman）
▪ Pressman: agility = “rapid and flexible response to change” + effective communication Pressman 定义：敏捷 = 对变化快速灵活的响应 + 高效的沟通
▪ It works best when 它在以下条件最有效:
▪ • The product is buildable in small increments 产品可按小增量构建
▪ • The customer is involved and gives feedback 客户参与并及时反馈
▪ • The team is competent, trusted, and self-organizing 团队有能力、被信任、可自组织
▪ • Culture tolerates change and ambiguity 文化上容忍变化与模糊
▪ Agility is not chaos — it is disciplined adaptability 敏捷不是混乱，而是有纪律的适应性
Software Engineering I · 2026-2027-1 · Ren Zheng
11

## Slide 12
Agile vs Plan-Driven
敏捷与计划驱动对比
Dimension 维度 | Plan-driven 计划驱动 | Agile 敏捷
Requirements 需求 | Stable, known early 稳定，早期明确 | Volatile, discovered 多变，逐步发现
Team size 团队规模 | Large, distributed 大型、分布式 | Small, co-located 小型、集中
Safety criticality 安全关键性 | High — needs heavy documentation 高，需厚重文档 | Low to moderate 中低
Culture 文化 | Order, predictability 秩序、可预测 | Chaos-tolerant, empowered 容忍混沌、授权
Documentation 文档 | Comprehensive 详尽 | “Just enough” 够用即可
Delivery 交付 | Big-bang at the end 末期一次性 | Small, frequent increments 小步高频交付
Software Engineering I · 2026-2027-1 · Ren Zheng
12

## Slide 13
Agility & the Cost of Change
敏捷与变更成本
▪ Traditional view 传统观点: cost of a change rises steeply with time — fix it late = pay much more 变更成本随时间陡升——越晚修改代价越大
▪ Agile claim 敏捷主张: with short cycles and continuous feedback, the curve flattens 通过短周期与持续反馈，曲线被“压平”
▪ Practices that flatten the curve 压平曲线的手段:
▪ • Early prototypes & tests catch problems sooner 原型与测试让问题更早暴露
▪ • Refactoring keeps design malleable 重构让设计保持可塑
▪ • Automated regression tests make change cheap to verify 自动化回归测试让变更的验证成本变低
▪ Debate 辩论: the flattening depends on discipline — without good practices, change still hurts 曲线能否压平取决于工程纪律
Software Engineering I · 2026-2027-1 · Ren Zheng
13

## Slide 14
Common Myths About Agile
敏捷常见迷思
▪ Myth 1: “Agile means no documentation” 迷思1：敏捷=无文档 → Reality: document “just enough” — what has lasting value 现实：写“够用”的文档——有长期价值才写
▪ Myth 2: “Agile means no planning” 迷思2：敏捷=无计划 → Reality: plan continuously, at multiple levels (release / iteration / day) 现实：多层持续地计划（发布/迭代/每日）
▪ Myth 3: “Agile only works for small teams” 迷思3：敏捷只适合小团队 → Reality: scales with frameworks (SAFe, LeSS), at a coordination cost 现实：可用规模化框架扩展，但有协调成本
▪ Myth 4: “Agile is a silver bullet” 迷思4：敏捷是银弹 → Reality: it is a trade-off space, not a cure-all 现实：它是一组权衡，不是万能药
Software Engineering I · 2026-2027-1 · Ren Zheng
14

## Slide 15
The Agile Landscape
敏捷方法家族一览
▪ Scrum — the most widely used framework; roles + events + artifacts 使用最广：角色+事件+工件（本课重点）
▪ Extreme Programming (XP) — engineering practices: TDD, pair programming, refactoring 工程实践派：测试驱动、结对编程、重构
▪ Kanban — visualize flow, limit work-in-progress, pull system 可视化流、限制在制品、拉动式
▪ Lean — eliminate waste, amplify learning, decide as late as possible 消除浪费、延迟决策
▪ This course: Scrum as the backbone; XP practices appear in construction weeks 本课程以 Scrum 为主线，工程实践在构建阶段展开
Software Engineering I · 2026-2027-1 · Ren Zheng
15

## Slide 16
Part C
The Scrum Framework Scrum 框架
Roles, artifacts, and events — the machine room of agility 角色、工件与活动——敏捷的机房

## Slide 17
What Is Scrum?
什么是 Scrum
▪ Name from rugby “scrum” — the whole team moves forward as one 名字来自橄榄球“并列争球”——全队作为一个整体推进
▪ A lightweight framework, not a process or technique 轻量级框架，不是具体过程或技术
▪ Built on empiricism 经验主义过程控制 — three pillars 三支柱:
▪ • Transparency 透明 — the process and work are visible to all 过程与工作对全员可见
▪ • Inspection 检视 — frequently check artifacts and progress 频繁检查工件与进度
▪ • Adaptation 适应 — adjust promptly when deviation is found 发现偏差立即调整
▪ Origin: Sutherland & Schwaber (1990s); canonical text: Scrum Guide (2020) 起源：Sutherland 与 Schwaber；权威文本：Scrum Guide 2020
Software Engineering I · 2026-2027-1 · Ren Zheng
17

## Slide 18
Five Scrum Values
Scrum 五价值观
▪ Commitment 承诺 — personally commit to achieving the team’s goals 个人承诺达成团队目标
▪ Focus 专注 — concentrate on the sprint work and goals 专注本冲刺的工作与目标
▪ Openness 开放 — be transparent about work and challenges 对工作与挑战保持透明
▪ Respect 尊重 — respect each other as capable, independent people 尊重彼此是有能力、独立的人
▪ Courage 勇气 — do the right thing and tackle tough problems 敢做正确的事，敢碰难题
▪ These values make the three pillars real in daily behavior 五价值观让三支柱落实为日常行为
Software Engineering I · 2026-2027-1 · Ren Zheng
18

## Slide 19
Three Roles
三种角色
Scrum Team
一个团队，三种角色 one team, three accountabilities
Product Owner
产品负责人
Maximizes product value · owns & orders the Backlog 最大化产品价值，管理并排序待办列表
Scrum Master
敏捷教练
Servant leader · removes obstacles · protects the process 服务型领导，排除障碍，守护流程
Developers
开发人员
Cross-functional, self-organizing · build the Increment 跨职能自组织，构建可用增量
Scrum Master is NOT a project manager — no task assignment, no hierarchy Scrum Master 不是项目经理——不分派任务、不搞层级
One team, three accountabilities — not three silos 一个团队，三种职责——不是三个部门
Software Engineering I · 2026-2027-1 · Ren Zheng
19

## Slide 20
Product Owner
产品负责人
▪ Owns and orders the Product Backlog — a single, visible, ordered list 独自管理并排序产品待办列表——唯一、可见、有序
▪ Represents the customer and business value 代表客户与业务价值
▪ Says “yes / no / later” to features — and is accountable for ROI 对功能说“是/否/以后”——对投资回报负责
▪ One person, not a committee; decisions must be respected 是一个人而非委员会；其决定必须被尊重
▪ In your SafeHome project: the PO role can rotate monthly SafeHome 项目中：PO 角色可每月轮换
Software Engineering I · 2026-2027-1 · Ren Zheng
20

## Slide 21
Scrum Master
敏捷教练
▪ Servant leader 服务型领导 — leads by serving the team, not by command 以服务而非命令来领导
▪ Ensures the team follows Scrum; coaches the organization 确保团队正确运用 Scrum；辅导组织
▪ Removes impediments: broken builds, missing environments, blockers 排除障碍：构建失败、环境缺失、外部阻塞
▪ Facilitates events as needed — but the team owns them 按需引导各活动——但活动属于团队
▪ NOT a project manager: no task assignment, no performance appraisals 不是项目经理：不分派任务、不做绩效考核
Software Engineering I · 2026-2027-1 · Ren Zheng
21

## Slide 22
Developers
开发人员
▪ Cross-functional: design, code, test, document — whatever the Increment needs 跨职能：设计、编码、测试、文档——增量需要什么就做什么
▪ Self-organizing: they decide HOW to turn Backlog into Increment 自组织：自行决定如何把待办变成增量
▪ Estimate and plan the work — nobody estimates “for” them 估算与计划由他们自己做——没人替他们估算
▪ Typical size: 10 or fewer — small enough to stay nimble 规模通常 ≤10 人，小到足够敏捷
▪ Quality is built in by the Developers’ Definition of Done 质量由开发人员的“完成定义”内建
Software Engineering I · 2026-2027-1 · Ren Zheng
22

## Slide 23
Three Artifacts
三大工件
▪ Product Backlog 产品待办列表 — everything potentially wanted in the product, ordered by value 产品可能需要的一切，按价值排序
▪ Sprint Backlog 冲刺待办列表 — why / what / how for this sprint (goal + selected items + plan) 本冲刺的目标+条目+计划
▪ Increment 增量 — a working, usable slice of product, meets the Definition of Done 可用的产品切片，满足完成定义
▪ Each artifact maximizes transparency — anyone can see the state 每个工件都最大化透明——任何人都能看到状态
▪ Commitment per artifact: Product Goal / Sprint Goal / Definition of Done 每个工件配一个承诺：产品目标/冲刺目标/完成定义
Software Engineering I · 2026-2027-1 · Ren Zheng
23

## Slide 24
The Product Backlog & User Stories
产品待办列表与用户故事
▪ Backlog items are often written as user stories 待办条目常写成“用户故事”:
▪ As a 〈role〉, I want 〈feature〉, so that 〈benefit〉. 作为〈角色〉，我想要〈功能〉，以便〈价值〉。
▪ Example 示例: As a homeowner, I want to arm the alarm from my phone, so that I feel safe when away 作为房主，我想用手机布防，以便外出时安心
▪ Ordering is value-driven: the most valuable items float to the top 排序由价值驱动：最有价值的条目浮到最上面
▪ Top items are “ready”: small, clear, testable; lower ones stay coarse 顶部条目“就绪”：小、清晰、可测试；下部保持粗粒度
▪ The backlog is a living artifact — it is re-ordered every sprint 待办列表是活的——每个冲刺都重新排序
Software Engineering I · 2026-2027-1 · Ren Zheng
24

## Slide 25
The Sprint Cycle
冲刺循环
Sprint Planning
冲刺计划 · what & how for this sprint 本冲刺做什么、怎么做
Daily Scrum
每日站会 · 15 min · every day 每天 15 分钟
Sprint Review
冲刺评审 · demo the Increment 演示可用增量
Sprint Retrospective
冲刺回顾 · improve the team 团队改进
THE SPRINT
固定 1–4 周 · 产出可用增量 fixed length, usable Increment
1 →
2 ↓
3 →
4 ↑
The cycle repeats — every sprint ends with a potentially shippable Increment 循环往复：每个冲刺结束都产出可交付的增量
All events happen inside the sprint — a fixed-length container 所有活动都发生在固定时长的冲刺之内
Software Engineering I · 2026-2027-1 · Ren Zheng
25

## Slide 26
Sprint Planning
冲刺计划会
▪ Time-boxed: max 8 hours for a one-month sprint (shorter for shorter sprints) 有时限：一个月冲刺最多 8 小时
▪ Three questions 三个问题:
▪ • Why is this sprint valuable? (Sprint Goal 冲刺目标) 本冲刺的价值是什么？
▪ • What can be done this sprint? (select Backlog items) 本冲刺能完成什么？
▪ • How will the work get done? (plan into tasks) 工作如何完成？
▪ Output: Sprint Backlog = goal + selected items + plan 产出：冲刺待办列表
Software Engineering I · 2026-2027-1 · Ren Zheng
26

## Slide 27
Daily Scrum
每日站会
▪ 15 minutes, same time, same place, every working day 每个工作日、同一时间、同一地点、15 分钟
▪ Inspect progress toward the Sprint Goal and adapt the day’s plan 检视冲刺目标进展，调整当日计划
▪ Each Developer answers three questions 每人回答三问:
▪ • What did I do yesterday? 昨天做了什么
▪ • What will I do today? 今天打算做什么
▪ • Do I see any impediment? 有没有障碍
▪ It is a planning meeting for Developers — NOT a status report to a boss 这是开发人员的计划会——不是向领导汇报
Software Engineering I · 2026-2027-1 · Ren Zheng
27

## Slide 28
Sprint Review
冲刺评审会
▪ Time-boxed: max 4 hours for a one-month sprint 有时限：一个月冲刺最多 4 小时
▪ The team presents the Increment to stakeholders — working software, not slides 向利益相关者演示增量——是可运行的软件，不是幻灯片
▪ Discuss: what was done, what changed, what is next in the Backlog 讨论：完成了什么、发生了什么变化、待办下一步
▪ Feedback flows back into the Product Backlog immediately 反馈立即回流到产品待办列表
▪ Working session, not a ceremony — collaboration over presentation 是协作的工作会，不是走过场的汇报
Software Engineering I · 2026-2027-1 · Ren Zheng
28

## Slide 29
Sprint Retrospective
冲刺回顾会
▪ Time-boxed: max 3 hours for a one-month sprint 有时限：一个月冲刺最多 3 小时
▪ The team inspects ITSELF — people, process, tools, culture 团队检视自身——人、过程、工具、协作
▪ Classic three columns 经典三栏:
▪ • What went well? 做得好的
▪ • What could be improved? 可改进的
▪ • What will we commit to change? 承诺改变的行动项
▪ Ends with concrete action items for the next sprint — not just feelings 以下个冲刺的具体行动项收尾——不空谈感受
Software Engineering I · 2026-2027-1 · Ren Zheng
29

## Slide 30
Velocity & Burndown
速度与燃尽图
Remaining work (story points) 剩余工作量
Sprint days 冲刺天数
— — ideal 理想线 —— actual 实际线
Burndown chart tracks remaining work daily; velocity = story points completed per sprint 燃尽图每日跟踪剩余工作；速度 = 每个冲刺完成的故事点数
Metrics guide planning — they do not judge individuals 度量用于计划，不用来评判个人
Software Engineering I · 2026-2027-1 · Ren Zheng
30

## Slide 31
Story Point Estimation
故事点估算
▪ Relative size, not hours — “this is twice as big as that” 相对大小而非小时数——“这个是那个的两倍大”
▪ Fibonacci-like scale: 1, 2, 3, 5, 8, 13, 20 … (bigger = fuzzier) 斐波那契数列：越大越模糊
▪ Planning Poker 规划扑克: everyone reveals an estimate simultaneously 所有人同时亮牌
▪ • Large spread = misunderstanding → discuss, re-vote 分歧大 = 理解不一致 → 讨论、重投
▪ • Consensus emerges fast and quietly surfaces hidden assumptions 快速达成共识，还能暴露隐藏假设
▪ Velocity 速度 = story points completed per sprint — used to forecast, not to compare teams 每冲刺完成的点数——用于预测，不用于团队间比较
Software Engineering I · 2026-2027-1 · Ren Zheng
31

## Slide 32
Definition of Done (DoD)
完成定义
▪ “Done” means more than “the code runs” “完成”不只是“代码能跑”:
▪ • Code written & peer-reviewed 代码已编写并通过同行评审
▪ • Unit tests written and passing 单元测试已写且通过
▪ • Integrated into the main build 已集成进主构建
▪ • Documentation updated 文档已更新
▪ The team agrees on its DoD and applies it to every Increment 团队共同约定 DoD，并适用于每个增量
▪ Weak DoD = hidden rework (“done-done” is not done) 弱 DoD = 隐性返工（“差不多完成”就是没完成）
Software Engineering I · 2026-2027-1 · Ren Zheng
32

## Slide 33
Scrum in 30 Seconds
Scrum 全景图
3 ROLES 三种角色
Product Owner
产品负责人
Scrum Master
敏捷教练
Developers
开发人员
5 EVENTS 五个事件
The Sprint (container) 冲刺本身：1–4周
Sprint Planning 冲刺计划
Daily Scrum 每日站会
Sprint Review 冲刺评审
Sprint Retrospective 冲刺回顾
3 ARTIFACTS 三大工件
Product Backlog 产品待办列表
ordered by value 按价值排序
Sprint Backlog 冲刺待办列表
this sprint’s plan 本冲刺计划
Increment 可用增量
meets the DoD 满足完成定义
Scrum = 3 roles + 5 events + 3 artifacts, bound together by empiricism Scrum = 三角色 + 五事件 + 三工件，以经验主义过程控制为纽带
Print this slide — it is the whole framework on one page 打印这一页：整个框架一图流
Software Engineering I · 2026-2027-1 · Ren Zheng
33

## Slide 34
Scrum vs Extreme Programming (XP)
Scrum 与 XP 对比
Scrum — manage the work 管理框架
▪ Framework: roles + events + artifacts 框架：角色+事件+工件
▪ Fixed-length sprints 固定长度冲刺
▪ No prescribed engineering practices 不规定工程实践
▪ Team self-organizes the HOW 由团队自组织决定怎么做
▪ Most common agile framework in industry 业界使用最广
XP — engineer the product 工程实践
▪ Practices: TDD, pair programming, refactoring, CI 实践：测试驱动、结对编程、重构、持续集成
▪ Iteration rhythm similar to sprints 迭代节奏与冲刺类似
▪ Prescribes HOW to build quality in 明确规定如何内建质量
▪ Customer on site 客户在现场
▪ Often combined: Scrum + XP practices 常常组合使用：Scrum 管过程 + XP 管工程
Software Engineering I · 2026-2027-1 · Ren Zheng
34

## Slide 35
When Agile Fits — and When Not
敏捷的适用边界
▪ Good fit 适用:
▪ • Unclear or fast-changing requirements 需求不明或变化快
▪ • Small, skilled, co-located, self-organizing teams 小型、有技能、集中、可自组织的团队
▪ • Product can be delivered in increments 产品可增量交付
▪ • Customer can participate continuously 客户能持续参与
▪ Poor fit 不适用:
▪ • Safety-critical systems requiring heavyweight certification 安全关键系统需重度认证
▪ • Fixed-price contracts with frozen scope 固定价格且范围冻结的合同
▪ Agile is a trade-off, not a religion — choose consciously 敏捷是权衡不是信仰——有意识地选择
Software Engineering I · 2026-2027-1 · Ren Zheng
35

## Slide 36
Part D
Class Activities 课堂活动
Practice the mindset before you need it 在需要之前先练起来

## Slide 37
Exercise 1 — Value or Violation?
练习1：符合还是违背宣言？
For each situation: does it ALIGN with the Agile Manifesto, or VIOLATE it? 判断每个情境符合还是违背敏捷宣言
Individual quick-fire · 4 min 个人快答 · 4 分钟
▪ A. Team skips ALL documentation — “working software is everything.” 跳过一切文档
▪ B. Customer attends sprint reviews and re-orders the backlog. 客户参加评审并重排待办
▪ C. Market shifts mid-project; team re-plans the next sprint. 市场突变，团队重计划
▪ D. Manager assigns daily tasks to each developer. 经理分派每日任务
▪ E. Two developers pair on the hardest story. 两人结对攻最难故事
▪ F. Shipping every 6 months because “the full plan was approved.” 半年一交付
Answer 答案: A violates (docs still matter — “just enough”); B aligns (customer collaboration); C aligns (responding to change); D violates (individuals & interactions / trust); E aligns (collaboration); F violates (early, frequent delivery)
Software Engineering I · 2026-2027-1 · Ren Zheng
37

## Slide 38
Exercise 2 — User Story Workshop
练习2：用户故事工坊
Write 3 user stories for SafeHome in the standard format, each with acceptance hints 为 SafeHome 写 3 条标准格式用户故事并附验收提示
Groups of 5–6 · 8 min → share 1 story per group 小组 · 8 分钟 → 每组分享 1 条
▪ Format 格式: As a 〈role〉, I want 〈feature〉, so that 〈benefit〉.
▪ Pick roles from: homeowner 房主 / security guard 保安 / installer 安装员 / parent 家长
▪ Think about: arming/disarming, sensors, alerts, video, scheduling, guest access 布防撤防、传感器、告警、视频、定时、访客权限
▪ Each story: one sentence + 2 acceptance criteria 每条故事一句话 + 2 条验收标准
Answer 答案: Example: As a homeowner, I want to receive an SMS alert when a motion sensor triggers while armed, so that I can react immediately. AC1: alert arrives < 10 s; AC2: message says which sensor fired.
Software Engineering I · 2026-2027-1 · Ren Zheng
38

## Slide 39
Exercise 3 — Mini Daily Scrum
练习3：迷你每日站会
Run a 3-minute Daily Scrum inside your group — every member answers the three questions 组内跑一场 3 分钟每日站会，人人回答三问
Groups · 5 min 小组 · 5 分钟
▪ Stand up — really stand 真的站起来 (it keeps it short)
▪ Each member: yesterday / today / impediments 每人：昨天 / 今天 / 障碍
▪ One member acts as Scrum Master: watch the 3-minute time-box and note impediments 一人扮演 Scrum Master：控时并记录障碍
▪ Debrief: what did the time-box change about the conversation? 反思：时限改变了什么？
Software Engineering I · 2026-2027-1 · Ren Zheng
39

## Slide 40
Today’s Summary
本课小结
▪ Agile = a mindset: 4 values + 12 principles — valuing the left over the right 敏捷是理念：四价值观 + 十二原则
▪ Agile ≠ no docs, no plan, no discipline — it is disciplined adaptability 敏捷 ≠ 无文档无计划，而是有纪律的适应
▪ Scrum = 3 roles + 5 events + 3 artifacts, on empiricism (transparency / inspection / adaptation) Scrum = 三角色+五事件+三工件
▪ The sprint is a fixed container that always yields a usable Increment 冲刺是固定容器，永远产出可用增量
▪ Agile has boundaries: safety-critical & frozen-scope projects fit poorly 敏捷有边界，安全关键与范围冻结项目并不适合
Key Takeaway 核心要点: Agility is how you respond to change — Scrum is one proven way to organize it. 敏捷是应对变化的方式，Scrum 是组织它的一种成熟框架。
Software Engineering I · 2026-2027-1 · Ren Zheng
40

## Slide 41
Homework
课后作业
▪ Read: Pressman Ch.3, agile development section 阅读 Pressman 第 3 章敏捷开发部分
▪ Skim: The Scrum Guide (2020) — 13 pages, the canonical text 通读 Scrum Guide 2020——仅 13 页权威文本
▪ Team task 团队任务: draft an initial Product Backlog for SafeHome — 8–10 user stories, ordered by value, top 3 with acceptance criteria 为 SafeHome 起草初始产品待办：8–10 条用户故事，按价值排序，前 3 条附验收标准
▪ Due: Week 4 — you will need it for project kickoff & team formation 下周项目启动与分组时要用
▪ Optional: watch one Scrum intro video and note 1 thing that surprised you 选做：看一段 Scrum 入门视频，记下 1 个惊讶点
Software Engineering I · 2026-2027-1 · Ren Zheng
41

## Slide 42
Thank You!
谢谢！
Next week: Requirements Inception & Elicitation — project kickoff & team formation 下周：需求启始与获取——项目启动与分组
See you next week! 下周见！